## QA_Checklist_Manual_Website
Category | Test ID | Section | Test Case Description | Priority | Expected Result | Actual Result | Status | Notes
--- | README | Scope | Manual website QA only: public pages + admin panel in the browser. | Info |  |  | Legend: Pass / Fail / Blocked / Not Tested | Login as super_admin, staff, and soccom separately for role-based tests.
Navigation | NAV-001 | Homepage | Verify Sto. Rosario Parish logo displays and links to home page | High | Logo visible in top-left corner; clicking it navigates to homepage |  | Not Tested
Navigation | NAV-002 | Homepage | Verify desktop navigation bar shows all menu items on scroll | High | Navbar shows Parish Services (dropdown), Community (dropdown), Track, Donate buttons; on scroll navbar background changes to white with shadow |  | Not Tested
Navigation | NAV-003 | Homepage | Verify Parish Services dropdown menu | Medium | Dropdown shows Mass Schedule, Submit Intention, Sacramental Inquiry sub-items; clicking navigates to correct page |  | Not Tested
Navigation | NAV-004 | Homepage | Verify Community dropdown menu | Medium | Dropdown shows Parish Events, Gallery, About Our Parish sub-items; clicking navigates to correct page |  | Not Tested
Navigation | NAV-005 | Homepage | Verify mobile hamburger menu | High | On mobile/tablet hamburger icon appears; clicking opens full-screen drawer menu with all navigation links |  | Not Tested
Navigation | NAV-006 | Homepage | Verify mobile menu Donate button | High | Mobile drawer has sticky Donate button at bottom that links to /donate |  | Not Tested
Navigation | NAV-007 | Homepage | Verify footer displays contact info and quick links | High | Footer shows parish name, address, contact numbers, office email, Facebook link, and quick links |  | Not Tested
Navigation | NAV-008 | Homepage | Verify announcements and bulletins reachable from homepage | Medium | Announcements and bulletins are not in navbar dropdown but accessible via homepage CTA links and footer |  | Not Tested
Navigation | NAV-009 | All Pages | Verify back to top button | Low | Floating back-to-top button appears after scrolling down; clicking scrolls smoothly to page top |  | Not Tested
Public Pages | PAGE-001 | Homepage | Verify hero section with background image and title | High | Full-screen hero with church background image, Sto. Rosario Parish title in Canterbury font, location subtitle |  | Not Tested
Public Pages | PAGE-002 | Homepage | Verify hero CTA buttons | High | Three buttons visible: Mass Schedule (ghost), Offer an Intention (gold), Parish Inquiry (ghost); all navigate correctly |  | Not Tested
Public Pages | PAGE-003 | Homepage | Verify next mass countdown/live mass slot component | High | Component shows next mass day/time with countdown timer and live mass indicator if applicable |  | Not Tested
Public Pages | LIVE-001 | Live Mass | Verify live mass embed during Sunday live window | High | On Sunday 9:55-11:15 AM, live mass section shows YouTube/Facebook tab toggle with working video embed |  | Not Tested
Public Pages | LIVE-002 | Live Mass | Verify sticky live mass banner on all pages | High | During live window, fixed bottom banner Live Mass is streaming now appears; clicking scrolls to #live-mass section |  | Not Tested
Public Pages | PAGE-004 | Homepage | Verify Quick Access cards grid | High | Four cards displayed: Mass Schedule, Offer Intention, Inquiry, Donate; all clickable with hover effects |  | Not Tested
Public Pages | PAGE-005 | Homepage | Verify parish stats strip | Medium | Stats strip shows 42+ Years of Service and 7 Weekly Masses with divider ornaments |  | Not Tested
Public Pages | PAGE-006 | Homepage | Verify upcoming events section | High | Shows up to 3 upcoming events with date badges, icons, times; View Full Schedule link navigates to events page |  | Not Tested
Public Pages | PAGE-007 | Homepage | Verify announcements carousel (featured) | High | Featured announcement shows with category badge, title, excerpt, Read more link, and optional recruitment/registration button |  | Not Tested
Public Pages | PAGE-008 | Homepage | Verify announcements carousel (pagination) | Medium | Carousel shows pagination dots and prev/next navigation; clicking changes visible cards |  | Not Tested
Public Pages | PAGE-009 | Homepage | Verify sacramental services grid | Medium | Six service cards shown: Baptism, Wedding, Confirmation, Funeral Mass, House Blessing, Car Blessing; each links to inquiry with type param |  | Not Tested
Public Pages | PAGE-010 | Homepage | Verify Offer a Mass Intention CTA section | Medium | Gold section with calligraphy cross, title Offer a Mass Intention, and two buttons (Submit Intention, Track Status) |  | Not Tested
Public Pages | PAGE-014 | Homepage | Verify View all announcements link | High | Homepage announcements section has View all announcements link that navigates to /announcements |  | Not Tested
Public Pages | PAGE-011 | About | Verify About page content loads | High | Page displays parish history, mission, possibly images and contact info |  | Not Tested
Public Pages | PAGE-012 | About | Verify Visit Parish Office anchor link | Medium | Link #visit-map in about page scrolls to map/contact section |  | Not Tested
Public Pages | PAGE-013 | About | Verify Google Maps embed or location info | Medium | Map or address information for Sto. Rosario Parish, Pacita Complex 1, San Pedro, Laguna is visible |  | Not Tested
Public Pages | SCHED-001 | Mass Schedule | Verify page loads with hero banner | High | Blue gradient hero section with title Mass Schedule and cross icon |  | Not Tested
Public Pages | SCHED-002 | Mass Schedule | Verify schedule category cards | High | Schedule cards grouped by type: Sunday Masses, Anticipated, Weekday Masses, Saturday Masses, Special Masses |  | Not Tested
Public Pages | SCHED-003 | Mass Schedule | Verify time chips display | High | Each schedule card shows time chips with formatted times (e.g., 6:30 AM) |  | Not Tested
Public Pages | SCHED-004 | Mass Schedule | Verify iCal download button | High | Download ICS button on each schedule card downloads .ics file with correct event data |  | Not Tested
Public Pages | SCHED-005 | Mass Schedule | Verify Google Calendar add button | High | Add to Google button opens Google Calendar with pre-filled event details |  | Not Tested
Public Pages | SCHED-006 | Mass Schedule | Verify Facebook link at bottom of page | High | Facebook link at bottom of page opens parish Facebook page in new tab |  | Not Tested
Public Pages | SCHED-007 | Mass Schedule | Verify empty state when no schedules | Low | When no schedules exist, displays No Schedules Available message with decorative cross |  | Not Tested
Public Pages | SCHED-008 | Mass Schedule | Verify responsive layout on mobile | High | On mobile, schedule sidebar becomes full-width at top with centered text; content below |  | Not Tested
Public Pages | EVENTS-001 | Events | Verify events list view | High | Default view shows events as cards with date badges, title, time slots, description, Google Cal and iCal links |  | Not Tested
Public Pages | EVENTS-002 | Events | Verify events calendar view | High | Calendar view shows month grid with event dots on dates; navigation between months works |  | Not Tested
Public Pages | EVENTS-003 | Events | Verify event detail page | High | Clicking event title navigates to /events/{id} showing full details including time slots and description |  | Not Tested
Public Pages | EVENTS-004 | Events | Verify empty state | Low | When no upcoming events, shows No Upcoming Events message |  | Not Tested
Public Pages | EVENTS-005 | Events | Verify View Announcements CTA at bottom | Medium | Gold button at bottom navigates to announcements page or Facebook |  | Not Tested
Public Pages | GALLERY-001 | Gallery | Verify gallery index page loads | High | Page displays gallery albums in grid layout or carousel with featured video option |  | Not Tested
Public Pages | GALLERY-002 | Gallery | Verify album browsing | High | Clicking an album opens album page showing images in a responsive grid/lightbox |  | Not Tested
Public Pages | GALLERY-003 | Gallery | Verify featured video | Medium | If album has featured video, video embed or thumbnail is displayed prominently |  | Not Tested
Public Pages | GALLERY-004 | Gallery | Verify image lightbox/modal | Medium | Clicking an image opens a modal/lightbox view with navigation arrows |  | Not Tested
Public Pages | GALLERY-005 | Gallery | Verify gallery all-items view | Medium | /gallery/all route shows admin-style gallery index with all images |  | Not Tested
Public Pages | ANNOUNCE-001 | Announcements | Verify announcements index page | High | List of announcements displayed with category badges and featured/recruitment tags |  | Not Tested
Public Pages | ANNOUNCE-002 | Announcements | Verify announcement detail page | High | Clicking announcement title opens single post with full content and category info |  | Not Tested
Public Pages | ANNOUNCE-003 | Announcements | Verify recruitment tag display | Medium | Announcements with is_recruitment=true show Recruitment badge and registration link if available |  | Not Tested
Public Pages | ANNOUNCE-004 | Announcements | Verify announcements index pagination | Medium | Index page paginates 12 announcements per page with working page navigation links |  | Not Tested
Public Pages | ANNOUNCE-005 | Announcements | Verify draft announcement hidden from public | High | Unpublished (draft) announcements do not appear on public index; direct URL returns 404 |  | Not Tested
Public Pages | ANNOUNCE-006 | Announcements | Verify announcement expiry date | High | Announcement with expires_at in the past is hidden from public index and detail page |  | Not Tested
Public Pages | ANNOUNCE-007 | Announcements | Verify featured announcement hero on homepage | High | is_featured=true announcement appears as hero card; remaining announcements appear in carousel |  | Not Tested
Public Pages | ANNOUNCE-008 | Announcements | Verify category badge color coding | Medium | Each category (Parish Life, Liturgical, Sacraments, Formation) shows distinct badge color and icon on cards |  | Not Tested
Public Pages | ANNOUNCE-009 | Announcements | Verify detail page breadcrumb navigation | Medium | Detail page shows Home > Announcements > Title breadcrumb; Announcements link returns to index |  | Not Tested
Public Pages | ANNOUNCE-010 | Announcements | Verify recent announcements sidebar on detail page | Medium | Detail page sidebar lists up to 5 other active announcements with clickable titles |  | Not Tested
Public Pages | BB-001 | Bulletins | Verify bulletins index page | High | Page shows list of downloadable parish bulletins with titles and dates |  | Not Tested
Public Pages | BB-002 | Bulletins | Verify bulletin download | High | Download button triggers file download of the bulletin PDF |  | Not Tested
Public Pages | INT-001 | Submit Intention | Verify page hero section | High | Blue gradient hero with title Submit Mass Intention, cross icon, and page description |  | Not Tested
Public Pages | INT-002 | Submit Intention | Verify form fields display | High | Form shows: Full Name (required), Email (required), Intention Category (dropdown, required), Mass Date (date picker, required), Service Time (dropdown, required), Intention Detail (textarea, required), Donation details (accordion) |  | Not Tested
Public Pages | INT-003 | Submit Intention | Verify intention categories dropdown | Medium | Dropdown shows: Thanksgiving, Birthday, Wedding Anniversary, Healing, Repose of the Soul, Special Intention, Other |  | Not Tested
Public Pages | INT-004 | Submit Intention | Verify mass date picker | High | Flatpickr date picker appears on click; minDate is today; date selection sets preferred date |  | Not Tested
Public Pages | INT-005 | Submit Intention | Verify service times update on date change | High | Sunday shows 6:30 AM, 8:30 AM, 10:00 AM, 3:00 PM, 4:30 PM, 6:00 PM; Saturday shows 6:30 AM, 6:00 PM; Weekdays show 6:00 PM only |  | Not Tested
Public Pages | INT-006 | Submit Intention | Verify donation accordion | High | Clicking Donation Details expands GCash/Bank toggle with QR code, account number (copyable), and bank details |  | Not Tested
Public Pages | INT-007 | Submit Intention | Verify form validation errors | High | When submitting empty form, red error borders and messages show for required fields; email field validates format |  | Not Tested
Public Pages | INT-008 | Submit Intention | Verify duplicate intention detection | Medium | When submitting duplicate for same requester, a warning modal shows with option to track existing or submit anyway |  | Not Tested
Public Pages | INT-009 | Submit Intention | Verify successful submission | High | On valid submit, success card displays with reference ID (INT-YYYY-XXXX), copy button, Track My Request link, and Submit Another button |  | Not Tested
Public Pages | INT-010 | Submit Intention | Verify reference ID copy function | Medium | Clicking copy icon copies the reference ID to clipboard and shows checkmark for 2 seconds |  | Not Tested
Public Pages | INT-011 | Submit Intention | Verify track status link from success | Medium | Track My Request button navigates to track-intention/{refId} with the submitted reference ID |  | Not Tested
Public Pages | INQ-001 | Inquiry | Verify page hero section | High | Blue gradient hero with title Parish Inquiries and cross icon |  | Not Tested
Public Pages | INQ-002 | Inquiry | Verify sidebar content | High | Left sidebar shows How It Works steps, contact numbers, and email |  | Not Tested
Public Pages | INQ-003 | Inquiry | Verify inquiry type dropdown | High | Dropdown shows categories: Baptism, First Communion, Confirmation, Wedding, Funeral Mass, Baptismal Certificate, Confirmation Certificate, Marriage Certificate, Car Blessing, House Blessing, Others |  | Not Tested
Public Pages | INQ-004 | Inquiry | Verify Baptism requirements display | Medium | When selecting Baptism, requirements box shows list of needed documents, schedule notes, dress code with NO CAPS warning |  | Not Tested
Public Pages | INQ-005 | Inquiry | Verify Wedding requirements display | Medium | When selecting Wedding, requirements box shows wedding documents, fees, schedule, and seminar info |  | Not Tested
Public Pages | INQ-006 | Inquiry | Verify Baptismal Certificate form fields | Medium | When selecting Baptism/Baptismal Certificate, structured input fields appear for name, birthdate, baptism date, birthplace, father, mother, purpose (instead of textarea) |  | Not Tested
Public Pages | INQ-007 | Inquiry | Verify preferred date field conditional display | High | For Baptism, Wedding, Funeral Mass types: date picker shows; for other types: date picker is hidden |  | Not Tested
Public Pages | INQ-008 | Inquiry | Verify form validation errors | High | When submitting empty form, red error borders and messages show for required fields |  | Not Tested
Public Pages | INQ-009 | Inquiry | Verify successful submission modal | High | On valid submit, success modal shows with reference ID (INQ-YYYY-XXXX), copy button, and Continue button |  | Not Tested
Public Pages | INQ-010 | Inquiry | Verify duplicate inquiry warning | Medium | When submitting duplicate inquiry, warning modal shows with option to track existing or submit anyway |  | Not Tested
Public Pages | INQ-011 | Inquiry | Verify service requirements display | High | Each inquiry type shows relevant document requirements when selected |  | Not Tested
Public Pages | INQ-012 | Inquiry | Verify Yes/No document confirmation for certificate requests | Medium | For Baptismal/Confirmation/Marriage Certificate types, YES/NO radio buttons appear asking if user wants a document |  | Not Tested
Public Pages | TRACK-001 | Track Status | Verify track status form | High | Input field accepts reference ID format and Check Status button |  | Not Tested
Public Pages | TRACK-002 | Track Status | Verify valid reference ID lookup | High | Entering a valid reference ID shows result card with status banner, name, submission date, preferred date, status with color coding (pending=orange, approved=green, rejected=red) |  | Not Tested
Public Pages | TRACK-003 | Track Status | Verify status color coding | Medium | Pending shows orange banner; Approved/Accepted shows green; Rejected/Declined shows red with rejection reason displayed |  | Not Tested
Public Pages | TRACK-004 | Track Status | Verify invalid reference ID | High | Entering invalid or non-existent reference ID shows appropriate error/validation message |  | Not Tested
Public Pages | TRACK-005 | Track Status | Verify status messages | Medium | Each status (pending/approved/rejected) shows appropriate informational message below detail grid |  | Not Tested
Public Pages | TRACK-006 | Track Status | Verify rejection reason display | Medium | Rejected inquiries show rejection reason in the result card |  | Not Tested
Public Pages | TRACK-007 | Track Status | Verify email lookup returns multiple records | High | Entering a valid email with multiple submissions shows combined list of intentions and inquiries |  | Not Tested
Public Pages | TRACK-008 | Track Status | Verify direct track URL without form | Medium | Navigating to /track-intention/{refId} directly shows status result without form submission |  | Not Tested
Public Pages | TRACK-009 | Track Status | Verify inquiry reference ID lookup | High | Entering valid INQ-YYYY-XXXX reference ID shows Sacramental Inquiry result with correct status |  | Not Tested
Public Pages | DON-001 | Donate | Verify page hero section | High | Dark blue hero with Support Our Parish title in gradient text, subtitle about stewardship |  | Not Tested
Public Pages | DON-002 | Donate | Verify payment method tabs | High | Three tabs visible: Online Payment, Scan QR, Bank Transfer; clicking switches content panels |  | Not Tested
Public Pages | DON-003 | Donate | Verify online payment form (PayMongo enabled) | High | When PayMongo is enabled: shows amount buttons (100, 500, 1,000, 5,000 PHP), custom amount input (min 100), purpose selector, donor name/email (optional), message, and Donate submit button |  | Not Tested
Public Pages | DON-004 | Donate | Verify online payment form (PayMongo disabled) | High | When PayMongo is disabled: shows Coming Soon placeholder with message about using QR or Bank Transfer tabs |  | Not Tested
Public Pages | DON-005 | Donate | Verify QR code tab | High | QR tab shows GCash number, account name, and QR code image (if configured) with copy buttons |  | Not Tested
Public Pages | DON-006 | Donate | Verify bank transfer tab | High | Bank tab shows BPI account details, and instruction to send proof to office email |  | Not Tested
Public Pages | DON-007 | Donate | Verify copy to clipboard functions | Medium | Clicking copy icon next to GCash number/name copies to clipboard and shows COPIED feedback |  | Not Tested
Public Pages | DON-008 | Donate | Verify donation amount validation | High | Submit button disabled when amount < 100 PHP; shows Select an amount text when no amount chosen |  | Not Tested
Public Pages | DON-009 | Donate | Verify donation success page | High | After successful PayMongo checkout, success page shows confirmation with donor name and amount |  | Not Tested
Public Pages | DON-010 | Donate | Verify donation receipt download | High | Signed URL route /donate/receipt/{donation} generates and displays PDF receipt |  | Not Tested
Public Pages | DON-011 | Donate | Verify donation cancel page | Medium | After cancelled PayMongo checkout, cancel page shows appropriate message |  | Not Tested
Public Pages | DON-012 | Donate | Verify Where your donation goes info | High | Right sidebar shows three info items: Church Maintenance, Pantry Community Outreach, Youth Ministry |  | Not Tested
Public Pages | DON-013 | Donate | Verify scripture quote | Low | Right sidebar shows 2 Corinthians 9:7 quote in styled card |  | Not Tested
Public Pages | CHAT-001 | Chatbot | Verify chatbot trigger button | High | Fixed bottom-left circular button with heart icon; clicking expands chat window |  | Not Tested
Public Pages | CHAT-002 | Chatbot | Verify chatbot welcome message | High | On first open, shows Peace be with you message with suggested chips: Mass Schedules, Offer Mass Intention, Sacramental Inquiry |  | Not Tested
Public Pages | CHAT-003 | Chatbot | Verify sending a message | High | Typing and sending a message displays it in chat bubble; bot responds with text and/or suggestions |  | Not Tested
Public Pages | CHAT-004 | Chatbot | Verify message timestamp display | Medium | Each message shows timestamp; if not today, shows date and time; if today, shows time only |  | Not Tested
Public Pages | CHAT-005 | Chatbot | Verify typing indicator | Medium | While bot is processing, shows animated dot loading indicator; when agent is connected, shows Agent is typing |  | Not Tested
Public Pages | CHAT-006 | Chatbot | Verify link formatting in bot responses | Medium | Bot responses render markdown links as clickable hyperlinks |  | Not Tested
Public Pages | CHAT-007 | Chatbot | Verify error handling | Medium | If API fails, shows error message with Retry button that re-sends last message |  | Not Tested
Public Pages | CHAT-008 | Chatbot | Verify suggested follow-up chips | High | After bot response, context-aware suggestion chips appear at bottom; clicking sends that suggestion as message |  | Not Tested
Public Pages | CHAT-009 | Chatbot | Verify character counter | Medium | Input field shows character counter (e.g., 500/1000); turns amber at 900+, red at 980+ |  | Not Tested
Public Pages | CHAT-010 | Chatbot | Verify handover to live agent | High | When bot suggests handover, shows two buttons: Submit Inquiry Form and Wait for Live Agent; clicking the latter initiates agent request |  | Not Tested
Public Pages | CHAT-011 | Chatbot | Verify live agent waiting state | Medium | After requesting agent, shows Waiting for a parish representative banner with amber status dot |  | Not Tested
Public Pages | CHAT-012 | Chatbot | Verify live agent connection | Medium | When admin accepts, status shows Live Agent Connected with blue dot; new messages from agent appear in chat |  | Not Tested
Public Pages | CHAT-013 | Chatbot | Verify agent timeout (120s) | Medium | If no agent connects within 120 seconds, shows timeout message with Go to Inquiry Page button |  | Not Tested
Public Pages | CHAT-014 | Chatbot | Verify conversation resolution | Medium | When conversation resolved, shows final system message and Start New Chat button |  | Not Tested
Public Pages | CHAT-015 | Chatbot | Verify session persistence | Medium | Chat state persists in sessionStorage across page reloads (messages, status, scroll position) |  | Not Tested
Public Pages | CHAT-016 | Chatbot | Verify unread message badge | Medium | When chat is closed and new messages arrive, red badge shows unread count on trigger button |  | Not Tested
Public Pages | CHAT-017 | Chatbot | Verify chat window scroll | Medium | Chat container auto-scrolls to bottom on new messages; preserves position if user scrolled up |  | Not Tested
Public Pages | CHAT-018 | Chatbot | Verify input disabled states | Medium | Input is disabled during loading or while waiting for agent; submit button disabled when input empty or loading |  | Not Tested
Public Pages | CHAT-019 | Chatbot | Verify agent typing indicator from backend | Medium | When admin is typing, Agent is typing shows in chat window |  | Not Tested
Public Pages | CHAT-020 | Chatbot | Verify agent pause/resume | Medium | When admin pauses, chat returns to AI mode with system message; when resumed, agent reconnects |  | Not Tested
Admin - Auth | AUTH-001 | Admin Login | Verify login page loads | High | /login form with email, password fields and Login button |  | Not Tested
Admin - Auth | AUTH-002 | Admin Login | Verify login with valid credentials | High | Entering correct email/password logs in and redirects to dashboard |  | Not Tested
Admin - Auth | AUTH-003 | Admin Login | Verify login with invalid credentials | High | Entering wrong credentials shows error message and stays on login page |  | Not Tested
Admin - Auth | AUTH-004 | Admin Login | Verify login throttle | High | After 5 failed attempts, login is throttled (rate limiting active) |  | Not Tested
Admin - Auth | AUTH-005 | Admin Login | Verify logout | High | Clicking logout button ends session and redirects to login page |  | Not Tested
Admin - Auth | AUTH-006 | Admin Login | Verify role-based access control | High | Non-authenticated users redirected to login; authenticated users see only their role features |  | Not Tested
Admin - Auth | AUTH-007 | Admin Login | Verify admin-portal redirect | Medium | Accessing /admin-portal/{path} performs 301 redirect to /internal/{path} |  | Not Tested
Admin - Auth | AUTH-008 | Admin Login | Verify super_admin can access all routes | High | super_admin role can access every admin panel route without restriction |  | Not Tested
Admin - Auth | AUTH-009 | Admin Login | Verify staff role access restrictions | High | staff role cannot access /internal/users or /internal/settings or /internal/logs |  | Not Tested
Admin - Auth | AUTH-010 | Admin Login | Verify soccom role access restrictions | High | soccom role cannot access /internal/users, /internal/intentions, or /internal/donations |  | Not Tested
Admin - Auth | AUTH-011 | Admin Login | Verify staff role content management restrictions | High | staff role cannot access /internal/announcements, /internal/schedules, /internal/events, /internal/gallery, or /internal/chats |  | Not Tested
Admin - Auth | AUTH-012 | Admin Login | Verify soccom and super_admin content access | High | soccom and super_admin can access announcements, schedules, events, gallery, highlights, and live chat |  | Not Tested
Admin - Dashboard | DASH-001 | Admin Dashboard | Verify dashboard loads after login | High | After login, /internal/dashboard shows overview cards with stats |  | Not Tested
Admin - Dashboard | DASH-004 | Admin Dashboard | Verify activity logs page | High | /internal/logs shows activity log table with timestamps, user, action, and details |  | Not Tested
Admin - Dashboard | DASH-005 | Admin Dashboard | Verify dashboard stats cards | Medium | Cards show counts for intentions, inquiries, donations, events, announcements |  | Not Tested
Admin - Dashboard | DASH-006 | Admin Dashboard | Verify dashboard loading states | Medium | Skeleton loaders show while dashboard data is being fetched |  | Not Tested
Admin - Mass Intentions | ADMIN-INT-001 | Admin Intentions | Verify intentions index page | High | /internal/intentions shows table of all mass intentions with search, filters, and status column |  | Not Tested
Admin - Mass Intentions | ADMIN-INT-002 | Admin Intentions | Verify intention creation form | High | /internal/intentions/create shows form with all fields: requester name, email, intention type, date, time, description, notes |  | Not Tested
Admin - Mass Intentions | ADMIN-INT-003 | Admin Intentions | Verify intention status update | High | Clicking status dropdown updates intention status; status change triggers email notification to requester |  | Not Tested
Admin - Mass Intentions | ADMIN-INT-004 | Admin Intentions | Verify batch status update | Medium | Select multiple intentions and batch update status via checkbox and batch action dropdown |  | Not Tested
Admin - Mass Intentions | ADMIN-INT-005 | Admin Intentions | Verify intention rejection reason | High | When rejecting an intention, rejection reason field is required and saved/displayed on tracking page |  | Not Tested
Admin - Mass Intentions | ADMIN-INT-006 | Admin Intentions | Verify intention show page | High | Clicking an intention shows detail page with full info, status history, and notes |  | Not Tested
Admin - Mass Intentions | ADMIN-INT-007 | Admin Intentions | Verify intentions email notification | High | On status change, requester receives email via IntentionStatusUpdated notification |  | Not Tested
Admin - Mass Intentions | ADMIN-INT-008 | Admin Intentions | Verify role access for intentions | Medium | Only super_admin and staff can access intentions CRUD; soccom cannot access |  | Not Tested
Admin - Mass Intentions | ADMIN-INT-009 | Admin Intentions | Verify intention search and filter | Medium | Intentions can be searched by name/email and filtered by status (pending/approved/rejected) |  | Not Tested
Admin - Mass Intentions | ADMIN-INT-010 | Admin Intentions | Verify intention reference ID format | Medium | Reference IDs follow format INT-YYYY-XXXX and are unique |  | Not Tested
Admin - Announcements | ADMIN-ANN-001 | Admin Announcements | Verify announcements index | High | /internal/announcements shows table of announcements with title, category, published status, and actions |  | Not Tested
Admin - Announcements | ADMIN-ANN-002 | Admin Announcements | Verify announcement creation | High | Create form with title, content, category, featured toggle, recruitment toggle, registration link |  | Not Tested
Admin - Announcements | ADMIN-ANN-003 | Admin Announcements | Verify announcement editing | Medium | Editing an announcement updates title, content, category, and all fields correctly |  | Not Tested
Admin - Announcements | ADMIN-ANN-004 | Admin Announcements | Verify announcement deletion | Medium | Deleting an announcement removes it from database and public listing |  | Not Tested
Admin - Announcements | ADMIN-ANN-005 | Admin Announcements | Verify recruitment field | Medium | Announcements with recruitment=True show Recruitment badge on public view and registration link if set |  | Not Tested
Admin - Announcements | ADMIN-ANN-006 | Admin Announcements | Verify category assignment | Medium | Announcements can be assigned categories: Parish Life, Liturgical, Sacraments, Formation with color-coded badges |  | Not Tested
Admin - Announcements | ADMIN-ANN-007 | Admin Announcements | Verify publish/draft toggle | High | Create and edit forms allow toggling is_published; draft announcements are hidden from public site |  | Not Tested
Admin - Announcements | ADMIN-ANN-008 | Admin Announcements | Verify expiry date field | High | expires_at field saves correctly; announcement auto-hides from public site after expiry datetime |  | Not Tested
Admin - Announcements | ADMIN-ANN-009 | Admin Announcements | Verify featured toggle on homepage | Medium | is_featured=true announcement appears as hero on homepage; toggling off removes hero placement |  | Not Tested
Admin - Announcements | ADMIN-ANN-010 | Admin Announcements | Verify role access for announcements | Medium | Only super_admin and soccom can access announcements CRUD; staff is denied |  | Not Tested
Admin - Events | ADMIN-EVT-001 | Admin Events | Verify events index page | High | /internal/events shows table of events with title, date, times, and actions |  | Not Tested
Admin - Events | ADMIN-EVT-002 | Admin Events | Verify event creation form | High | Create form with title, description, event date, multiple time slots (with title+time), and URL field for external links |  | Not Tested
Admin - Events | ADMIN-EVT-003 | Admin Events | Verify event time slots | Medium | Multiple time slots can be added; each slot has title and time fields |  | Not Tested
Admin - Events | ADMIN-EVT-004 | Admin Events | Verify event editing | Medium | Editing updates all event fields including time slots and saves correctly |  | Not Tested
Admin - Events | ADMIN-EVT-005 | Admin Events | Verify event deletion | Medium | Deleting removes event from database and public event listing |  | Not Tested
Admin - Events | ADMIN-EVT-006 | Admin Events | Verify event publish/draft toggle | High | Unpublished events do not appear on public events page; published events are visible |  | Not Tested
Admin - Gallery | ADMIN-GAL-001 | Admin Gallery | Verify albums index | High | /internal/gallery shows list of albums with cover image, title, photo count, and featured video status |  | Not Tested
Admin - Gallery | ADMIN-GAL-002 | Admin Gallery | Verify album creation | High | Create new album with title and description |  | Not Tested
Admin - Gallery | ADMIN-GAL-003 | Admin Gallery | Verify image upload to album | High | Add Images form allows multiple file upload; uploads are queued via UploadGalleryMediaJob |  | Not Tested
Admin - Gallery | ADMIN-GAL-004 | Admin Gallery | Verify image deletion | Medium | Deleting an image removes it from album and storage |  | Not Tested
Admin - Gallery | ADMIN-GAL-005 | Admin Gallery | Verify featured video | Medium | Setting a featured video URL displays video embed on public album view |  | Not Tested
Admin - Gallery | ADMIN-GAL-006 | Admin Gallery | Verify album publish/draft toggle | High | Draft albums (is_published=false) are hidden from public gallery; published albums are visible |  | Not Tested
Admin - Schedules | ADMIN-SCHED-001 | Admin Schedules | Verify schedules index | High | /internal/schedules shows table of mass schedules with day(s), time(s), type, title |  | Not Tested
Admin - Schedules | ADMIN-SCHED-002 | Admin Schedules | Verify schedule creation | High | Create form with mass type (sunday/anticipated/weekday/saturday/special), day of week, time, title fields |  | Not Tested
Admin - Schedules | ADMIN-SCHED-003 | Admin Schedules | Verify schedule editing | Medium | Editing updates day(s), time(s), and type correctly |  | Not Tested
Admin - Schedules | ADMIN-SCHED-004 | Admin Schedules | Verify schedule deletion | Medium | Deleting a schedule removes it from the public mass schedule page |  | Not Tested
Admin - Schedules | ADMIN-SCHED-005 | Admin Schedules | Verify multiple days and times | Medium | A single schedule can have multiple day_of_week values and multiple time entries |  | Not Tested
Admin - Schedules | ADMIN-SCHED-006 | Admin Schedules | Verify iCal export from admin | Medium | Each schedule can generate iCal file with correct recurrence rule (RRULE) for weekly masses |  | Not Tested
Admin - Inquiries | ADMIN-INQ-001 | Admin Inquiries | Verify inquiries index | High | /internal/inquiries shows table of all inquiries with name, type, status, and actions |  | Not Tested
Admin - Inquiries | ADMIN-INQ-002 | Admin Inquiries | Verify inquiry detail view | High | Clicking an inquiry shows detail page with full info, requirements, and status |  | Not Tested
Admin - Inquiries | ADMIN-INQ-003 | Admin Inquiries | Verify inquiry accept | High | Accept button changes status to accepted and sends notification email to requester |  | Not Tested
Admin - Inquiries | ADMIN-INQ-004 | Admin Inquiries | Verify inquiry decline | High | Decline button opens reason modal; status changes to declined with reason saved and email sent |  | Not Tested
Admin - Inquiries | ADMIN-INQ-005 | Admin Inquiries | Verify rejection reason display | Medium | Declining requires a rejection reason that displays on public tracking page |  | Not Tested
Admin - Inquiries | ADMIN-INQ-006 | Admin Inquiries | Verify role access for inquiries | Medium | Only super_admin, staff, and soccom can access inquiries; super_admin+staff see intentions only |  | Not Tested
Admin - Inquiries | ADMIN-INQ-007 | Admin Inquiries | Verify inquiry filtering | Medium | Inquiries can be filtered by type (Baptism, Wedding, etc.) and status (pending/accepted/declined) |  | Not Tested
Admin - Inquiries | ADMIN-INQ-008 | Admin Inquiries | Verify inquiry email notification | High | On accept/decline, requester receives email via InquiryStatusUpdated notification |  | Not Tested
Admin - Donations | ADMIN-DON-001 | Admin Donations | Verify donations index page loads | High | /internal/donations shows donations table with donor, amount, purpose, method, status, date, and reference |  | Not Tested
Admin - Donations | ADMIN-DON-002 | Admin Donations | Verify donation stats cards | High | Page shows Total Received, Today, and Total Donations stat cards with correct calculated values |  | Not Tested
Admin - Donations | ADMIN-DON-003 | Admin Donations | Verify donation status display | Medium | Table shows correct status badges for pending, paid, failed, and cancelled donations |  | Not Tested
Admin - Donations | ADMIN-DON-004 | Admin Donations | Verify role access for donations | High | Only super_admin and staff can access /internal/donations; soccom is denied |  | Not Tested
Admin - Live Chat | ADMIN-CHAT-001 | Admin Live Chat | Verify chats index page | High | /internal/chats shows list of chat sessions with participant info, last message, status |  | Not Tested
Admin - Live Chat | ADMIN-CHAT-002 | Admin Live Chat | Verify chat session detail | High | Clicking a chat session opens conversation view with full message history |  | Not Tested
Admin - Live Chat | ADMIN-CHAT-003 | Admin Live Chat | Verify admin reply | High | Admin can type and send replies; messages appear in user chat window in real-time via polling |  | Not Tested
Admin - Live Chat | ADMIN-CHAT-004 | Admin Live Chat | Verify resolve chat | High | Resolve button marks chat as resolved; user chat shows end message and Start New Chat button |  | Not Tested
Admin - Live Chat | ADMIN-CHAT-005 | Admin Live Chat | Verify pause/resume chat | Medium | Pause button puts chat back to AI mode with system message; Resume reconnects agent |  | Not Tested
Admin - Live Chat | ADMIN-CHAT-006 | Admin Live Chat | Verify admin typing indicator | Medium | When admin is typing, user chat shows Agent is typing indicator |  | Not Tested
Admin - Live Chat | ADMIN-CHAT-009 | Admin Live Chat | Verify admin accept agent request | High | When user requests live agent, admin sees notification and can click to connect |  | Not Tested
Admin - Live Chat | ADMIN-CHAT-010 | Admin Live Chat | Verify live chat role access | Medium | super_admin and soccom can access live chat admin pages; staff is denied |  | Not Tested
Admin - Users | ADMIN-USER-001 | Admin Users | Verify users index page | High | /internal/users shows table of users with name, email, role, active status, and actions |  | Not Tested
Admin - Users | ADMIN-USER-002 | Admin Users | Verify user creation | High | Add user form with name, email, password, role (super_admin/staff/soccom), is_active checkbox |  | Not Tested
Admin - Users | ADMIN-USER-003 | Admin Users | Verify user editing | Medium | Editing a user updates name, email, password (optional), role, and active status correctly |  | Not Tested
Admin - Users | ADMIN-USER-004 | Admin Users | Verify user deletion | Medium | Deleting a user removes them from the system (soft delete) |  | Not Tested
Admin - Users | ADMIN-USER-005 | Admin Users | Verify role-based user access | High | Only super_admin can access user management; staff and soccom are denied |  | Not Tested
Admin - Settings | ADMIN-SET-001 | Admin Settings | Verify settings index page | High | /internal/settings shows form with global settings: parish info, contact details, payment methods, social links |  | Not Tested
Admin - Settings | ADMIN-SET-002 | Admin Settings | Verify settings update | High | Updating settings saves to database and reflects immediately on public pages |  | Not Tested
Admin - Settings | ADMIN-SET-003 | Admin Settings | Verify GCash number setting | Medium | Setting GCash number in admin reflects on donate page QR tab and intention form donation section |  | Not Tested
Admin - Settings | ADMIN-SET-004 | Admin Settings | Verify QR code upload | Medium | QR code image can be uploaded/selected and displays on donate QR tab |  | Not Tested
Admin - Settings | ADMIN-SET-005 | Admin Settings | Verify role access for settings | High | Only super_admin can access settings; staff and soccom are denied |  | Not Tested
Admin - PPT Tools | ADMIN-PPT-001 | Admin PPT Tools | Verify PPT generation form | High | PPT tools page shows form to select mass schedule and generate presentation |  | Not Tested
Admin - PPT Tools | ADMIN-PPT-002 | Admin PPT Tools | Verify PPT preview | High | Generate PPT button creates presentation; preview link opens downloadable preview |  | Not Tested
Admin - PPT Tools | ADMIN-PPT-003 | Admin PPT Tools | Verify Google Slides creation | High | Create Google Slides button opens Google OAuth flow and creates slides from mass schedule |  | Not Tested
Admin - PPT Tools | ADMIN-PPT-004 | Admin PPT Tools | Verify role access for PPT tools | Medium | super_admin, staff, and soccom can access PPT tools |  | Not Tested
Admin - Video Highlights | ADMIN-VH-001 | Admin Highlights | Verify highlights index page | High | /internal/highlights shows list of video highlights with title, URL, and sort order |  | Not Tested
Admin - Video Highlights | ADMIN-VH-002 | Admin Highlights | Verify highlight creation | High | Create form with title, video URL/path, and embed code |  | Not Tested
Admin - Video Highlights | ADMIN-VH-003 | Admin Highlights | Verify highlight reordering | Medium | Drag-and-drop reordering persists new sort order to database |  | Not Tested
Admin - Video Highlights | ADMIN-VH-004 | Admin Highlights | Verify highlight display on gallery | Medium | Video highlights appear on public gallery pages with proper embed |  | Not Tested
Admin - Video Highlights | ADMIN-VH-005 | Admin Highlights | Verify role access for highlights | Medium | Only super_admin and soccom can manage video highlights |  | Not Tested
Admin - Video Highlights | ADMIN-VH-006 | Admin Highlights | Verify highlight publish/draft toggle | High | Unpublished highlights are hidden from public gallery; published highlights display with embed |  | Not Tested
Responsive Design | RESP-001 | All Pages | Verify homepage on mobile (375px) | High | All sections stack vertically; mobile drawer menu works; hero text scales down; quick actions grid becomes 2 columns |  | Not Tested
Responsive Design | RESP-002 | All Pages | Verify homepage on tablet (768px) | High | Navbar switches to mobile mode; events grid shows 2 columns; content adjusts appropriately |  | Not Tested
Responsive Design | RESP-003 | All Pages | Verify homepage on desktop (1440px+) | High | Full-width layout; 4-column quick actions grid; 3-column events grid; all hover effects work |  | Not Tested
Responsive Design | RESP-004 | All Pages | Verify mass schedule responsive design | High | On mobile, schedule sidebar becomes full-width at top with centered text; content stacks below |  | Not Tested
Responsive Design | RESP-005 | All Pages | Verify events calendar on mobile | High | Calendar view scrolls horizontally; grid cells remain readable; event modal is full-width |  | Not Tested
Responsive Design | RESP-006 | All Pages | Verify gallery responsive grid | High | Gallery images stack to single column on mobile, 2-3 columns on tablet, 4+ on desktop |  | Not Tested
Responsive Design | RESP-007 | All Pages | Verify chatbot responsive sizing | High | Chat window width adjusts: full width minus padding on mobile, fixed 410px max on desktop |  | Not Tested
Responsive Design | RESP-008 | All Pages | Verify donation page responsive | High | On mobile, donation info panel moves below payment form; tabs may stack vertically |  | Not Tested
Responsive Design | RESP-009 | All Pages | Verify inquiry form responsive | High | On mobile, sidebar moves to top or collapses; form fields stack to single column |  | Not Tested
Responsive Design | RESP-010 | All Pages | Verify track status page responsive | High | Track form and result card are centered and readable on all screen sizes |  | Not Tested
Responsive Design | RESP-011 | All Pages | Verify admin dashboard responsive | High | Admin tables become horizontally scrollable on mobile; sidebar collapses to icons |  | Not Tested
Security & Validation | SEC-002 | All Forms | Verify form input sanitization | High | Form inputs are sanitized; XSS payloads in name/message fields are escaped on display |  | Not Tested
Security & Validation | SEC-003 | All Forms | Verify rate limiting on submissions | High | Mass intention and inquiry forms have throttle:submissions middleware; excessive submissions are blocked |  | Not Tested
Security & Validation | SEC-004 | All Forms | Verify email format validation | Medium | Email fields validate proper format; invalid emails show error message |  | Not Tested
Security & Validation | SEC-005 | All Forms | Verify required field validation | High | All required fields show validation errors when left empty |  | Not Tested
Security & Validation | SEC-008 | Admin Auth | Verify signed URL for donation receipt | Medium | Donation receipt route uses signed middleware; invalid signatures are rejected |  | Not Tested
Performance | PERF-001 | All Pages | Verify page load time | Medium | Homepage loads in under 3 seconds on fast connection; Largest Contentful Paint under 2.5s |  | Not Tested
Performance | PERF-002 | All Pages | Verify image optimization | Medium | Images use fetchpriority, decoding=async, and proper width/height attributes |  | Not Tested
Performance | PERF-003 | All Pages | Verify font loading | Medium | Canterbury font is preloaded via preload as=font; web fonts load without FOIT |  | Not Tested
Performance | PERF-004 | All Pages | Verify Vite build assets are loaded | High | Built CSS and JS files load from /public/build/ with correct manifest paths |  | Not Tested
Performance | PERF-005 | All Pages | Verify lazy loading on gallery | Medium | Gallery images below the fold are lazy-loaded |  | Not Tested
SEO & Accessibility | SEO-001 | All Public Pages | Verify meta description tag | High | Each public page has a unique meta description tag in the head |  | Not Tested
SEO & Accessibility | SEO-002 | All Public Pages | Verify Open Graph tags | Medium | Pages include og:title, og:description, og:image tags for social sharing |  | Not Tested
SEO & Accessibility | SEO-003 | All Pages | Verify sitemap.xml exists and is valid | High | /sitemap.xml returns valid XML including /, /about, /mass-schedule, /submit-intention, /inquiry, /events, /gallery, /donate, /announcements, /bulletins, /track |  | Not Tested
SEO & Accessibility | SEO-004 | All Pages | Verify robots.txt | High | /robots.txt exists and disallows admin/internal paths |  | Not Tested
SEO & Accessibility | SEO-005 | All Pages | Verify favicon display | Medium | favicon.ico loads in browser tab and is properly linked in head |  | Not Tested
SEO & Accessibility | SEO-006 | All Pages | Verify ARIA labels on interactive elements | Medium | Buttons, links, and form elements have appropriate aria-label attributes |  | Not Tested
SEO & Accessibility | SEO-007 | All Pages | Verify heading hierarchy | Medium | Pages follow H1-H2-H3 hierarchy; only one H1 per page |  | Not Tested
SEO & Accessibility | SEO-008 | All Pages | Verify skip to content / keyboard navigation | Medium | Key interactive elements are reachable via Tab key; focus rings are visible |  | Not Tested
SEO & Accessibility | SEO-011 | All Pages | Verify skip to main content link | Medium | Skip to main content link is first focusable element; activating it jumps focus to #main-content |  | Not Tested
SEO & Accessibility | SEO-009 | All Pages | Verify alt text on images | High | All content images have descriptive alt text; decorative images have empty alt |  | Not Tested
SEO & Accessibility | SEO-010 | Chatbot | Verify chatbot accessibility | Medium | Chatbot has aria-label on trigger button, proper focus management, and escape key closes window |  | Not Tested
Email & Notifications | EMAIL-007 | Inquiry Submitted | Verify notification appears in admin panel | Medium | New inquiries trigger database notifications visible in admin dashboard SSE stream |  | Not Tested
Email & Notifications | EMAIL-008 | Intention Submitted | Verify notification appears in admin panel | Medium | New intentions trigger database notifications visible in admin dashboard SSE stream |  | Not Tested
Integration | INTEGR-001 | Google Services | Verify Google OAuth login flow | High | Google auth endpoint initiates OAuth; callback stores tokens correctly |  | Not Tested
Integration | INTEGR-002 | Google Services | Verify Google Slides creation | High | PPT generation can create Google Slides from mass schedule data via API |  | Not Tested
Integration | INTEGR-003 | Google Services | Verify Google Drive file access | Medium | Generated slides/PPTs are accessible via Google Drive with correct permissions |  | Not Tested
Integration | INTEGR-004 | PayMongo | Verify PayMongo checkout redirect | High | Donation checkout creates PayMongo checkout session and redirects to payment page |  | Not Tested
Integration | INTEGR-006 | AI Chatbot | Verify Groq/OpenRouter API connection | High | Chatbot sends/receives messages via AI API; responses are contextually relevant |  | Not Tested
Integration | INTEGR-008 | Supabase Storage | Verify Supabase storage integration | High | Images and assets are served from Supabase S3-compatible storage URLs |  | Not Tested
Error Handling | ERR-001 | 404 Page | Verify 404 page displays | High | Accessing non-existent route shows styled 404 error page with return home link |  | Not Tested
Error Handling | ERR-002 | 403 Page | Verify 403 page displays | High | Accessing unauthorized route shows styled 403 error page |  | Not Tested
Error Handling | ERR-003 | 401 Page | Verify 401 page displays | High | Accessing protected route without auth shows styled 401 page |  | Not Tested
Error Handling | ERR-004 | 500 Page | Verify 500 page displays | High | Server errors show styled 500 page without exposing stack traces |  | Not Tested
Error Handling | ERR-005 | Chatbot | Verify chatbot API error handling | Medium | If chatbot API is down, shows friendly error message with retry option |  | Not Tested
Error Handling | ERR-006 | Donation | Verify PayMongo API error handling | Medium | If PayMongo API fails, shows error message and suggests alternative payment methods |  | Not Tested
Error Handling | ERR-007 | All Forms | Verify server-side validation errors display in UI | High | Validation errors from server are shown inline next to the relevant field |  | Not Tested
Data Integrity | DATA-001 | Mass Intentions | Verify unique reference ID generation | High | Each mass intention gets a unique INT-YYYY-XXXX reference ID |  | Not Tested
Data Integrity | DATA-002 | Inquiries | Verify unique reference ID generation | High | Each inquiry gets a unique INQ-YYYY-XXXX reference ID |  | Not Tested
Data Integrity | DATA-003 | Mass Intentions | Verify duplicate detection logic | Medium | Duplicate check looks at email + intention type + date within a time window |  | Not Tested
Data Integrity | DATA-004 | Inquiries | Verify duplicate detection logic | Medium | Duplicate check looks at email + inquiry type within a time window |  | Not Tested
Cross-Browser Testing | CB-001 | All Pages | Verify Chrome (latest) | High | All features work correctly on latest Chrome (desktop and mobile) |  | Not Tested
Cross-Browser Testing | CB-002 | All Pages | Verify Firefox (latest) | High | All features work correctly on latest Firefox |  | Not Tested
Cross-Browser Testing | CB-003 | All Pages | Verify Safari (latest) | Medium | All features work correctly on latest Safari (desktop and iOS) |  | Not Tested
Cross-Browser Testing | CB-004 | All Pages | Verify Edge (latest) | Medium | All features work correctly on latest Microsoft Edge |  | Not Tested
Cross-Browser Testing | CB-005 | Admin Panel | Verify admin panel on mobile | Low | Admin panel is usable on mobile; tables scroll horizontally; forms are accessible |  | Not Tested